Dance Performance in Mangaung Community

Prepared by: DevCore

Group Members & Roles:

- Tshepang Paballo Mofokeng : Project Manager

- Malefetsane Tabi : Risk Manager

- Luyanda Mfuphi : Communications Officer

- Magaleng Johannes Madike : Financial Controller

- Ranthako Richard Machaea : Content Director

- Mahlale Molefi : Technical Lead

Lecturer: O.P Tsumake

Institution: Central University of Technology

Submission Date : Tuesday ,21 April 2026

- Project Charter(Initiation)

Project Title: Dance Performances in Mangaung Community

Project start date: 20 March 2026   	Project end date: 21 April 2026

Budget information: The project budget is R800. Transport fee R300, Data/Internet R200. Printing R100 and Miscellaneous of R200.

Project manager: Tshepang Paballo Mofokeng    24008826@stud.cut.ac.za.

| Name | Role | Position | Contact Information |
| --- | --- | --- | --- |
| Tshepang Paballo Mofokeng | Project Manager | Project coordinator | 224008826@stud.cut.ac.za |
| Malefetsane Tabi | Risk Manager | Risk Analyst | 224124912@stud.cut.ac.za |
| Luyanda Mfuphi | Communications Officer | Communications Officer | 224053974@stud.cut.ac.za |

Project objectives:  This project focuses on researching and showcasing dance forms within the Mangaung community. It will combine cultural research with digital media to preserve and promote local dance traditions.

Main Project success criteria: To complete the project within the domain of the triple constraints (scope, time, and cost), while carefully ensuring that that:

- Completion of research on at least 3 dances is completed.

- A functional website is developed.

- At least 3–4 performance videos are uploaded.

- Stakeholder engagement achieved

- Project delivered before 21 April 2026

Approach:

- Identify and document at least three dance styles in Mangaung.

- Research their history, cultural significance, and artistic.

- Create a digital platform(Website) showcasing findings.

- Engage local stakeholders and collect multimedia content.

| Magaleng Johannes Madike | Financial Controller | Financial Controller | 221023288@stud.cut.ac.za |
| --- | --- | --- | --- |
| Ranthako Richard Machaea | Content Director | Content Director | 222015743@stud.cut.ac.za |
| Mahlale Molefi | Technical Lead | Programmer | 224008698@stud.cut.ac.za |
| O.P Tsumake | Sponsor | Director | otsumake@cut.ac.za |

Sign Off: Tshepang and OP

Commence: “Through rhythm, movement, and unity, we bring the stories of Mangaung to life.”

- Stakeholder Register

| Stakeholder | Role in Project | Interest | Influence | Communication Method |
| --- | --- | --- | --- | --- |
| O.P Tsumake(Lecturer) | Project Sponsor | High | High | In class/Email |
| DevCore Team Members | Project Team | High | High | WhatsApp Meetings |
| Dance Groups | Provide interviews & performance | High | Medium | Email |
| Mangaung Community | Audience | Medium | Medium | In Person |
| Website Users | View and engage with content | Medium | Low | Website |

- Work Breakdown Structure (Planning)

- Initiation

  - Develop Project Charter

  - Identify Stakeholders

- Planning

  - Create WBS

  - Develop Risk Register

  - Develop Quality Plan

  - Create Project Schedule(Gantt Chart)

- Execution

  - Conduct Research on Dance Types

  - Contract Dance Groups

  - Schedule Interviews

  - Record Interviews

  - Record Dance Performances

  - Collect photos and Videos

- Website Development

  - Design Website Layout

  - Create Dance Pages

  - Upload Content

- Monitoring and Control

  - Track Project Progress

  - Update Schedule

  - Manage Risks

- Closing

  - Compile Final Report

  - Prepare Presentation

  - Submit Project

- Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| No access to dancers | High | Contract multiple groups |
| Poor internet | Medium | Work offline & upload later |
| Time constraints | High | Follow schedule strictly |
| Equipment failure | Medium | Use backup devices |
| Lack of permissions | High | Get consent forms early |
| Poor quality videos/audio recording | Medium | Test equipment before filming. Record multiple takes. |
| Team members not completing tasks | High | Assign clear responsibilities. Set deadlines and monitor progress. |
| Website technical issues | Medium | Use simple platforms. Save backups of content. |
| Loss of data (video or photos) | High | Save copies on multiple devices. |
| Miscommunication within the team. | Medium | Use one main communication platform. |

- Communication Plan

| Stakeholder | Information Shared | Method | Frequency | Responsible |
| --- | --- | --- | --- | --- |
| DevCore Team | Task updates, progress ,deadlines and responsibilities | WhatsApp/Meetings | Daily | Project Manager |
| Lecturer | Issues/Project Progress | Email/in class | As needed | Project Manager |
| Dance Groups | Permissions and scheduling interviews | Email | As needed | Communications Officer |
| Website Users | Project content, dance information | Website | Continuous | Technical Lead |
| Mangaung Community | Awareness of project and cultural content | Website/Social Media | Continuous | Content Director |

Effective communication will be maintained throughout the project to ensure all stakeholders are informed, aligned and able to contribute to the successful completion of the project.

- Quality Plan

Quality Objectives:

- Ensure accurate and well researched information on all dance types.

- Produce clear, high quality videos and images.

- Develop a functional and user friendly website.

- Ensure all links and media work correctly.

Quality Standards:

- Information must be relevant and factually correct.

- Video must have clear audio and visuals.

- Website must be easy to navigate.

- Content must be well organized and professional.

Quality Control Measures:

- Review all content before uploading.

- Test videos, links, and website functionality.

- Get feedback from group members.

- Make corrections where necessary.

- Execution Evidence

Figure 1: Communication with group members regarding task allocation

Figure 2: Communication with dance group to arrange interview and filming

Figure 3: Conducting interview with Tswana dance group

- Monitoring & Control

Progress Monitoring:

- Regular communication was maintained through WhatsApp to track daily progress.

- Tasks were assigned and followed up by the project manager.

- Team members provided updates on their responsibilities.

Schedule Control:

- The project timeline was reviewed and adjusted when necessary.

- Tasks were completed in parallel to meet the deadline.

- Delays in response from dance groups were managed by implementing backup plans.

Risk Monitoring:

- Identified risks were continuously reviewed.

- Team members communicated any issues immediately.

- Mitigation strategies were applied where needed.

Evidence of Monitoring:

- Updates on task completion.

- Website development progress.

- Closing Report & Lessons Learned

Project Summary: The project focused on exploring and documenting different dance styles within the Mangaung community, including Tswana Dance, Famo and Mohobelo . The team successfully combined research and practical engagement by conducting interviews and recording performances. A digital platform was developed to present the findings in a structured and engaging way. Overall, the project was completed within the given timeframe.

Objectives Achieved:

- Developed a functional website.

- Compiled and organized all project documentation.

- Collected multimedia content (videos and images).

- Identified and researched multiple dance types

Challenges Faced:

- Limited time to complete all project requirements.

- Delays in responses from some dance groups.

- Scheduling conflicts for interviews and filming.

Solutions Implemented:

- Divided tasks among team members to improve efficiency.

- Used backup plans when stakeholders were unavailable.

- Conducted tasks in parallel to meet deadlines.

Lessons Learned:

- Effective communication is essential for team coordination.

- Time management is critical in meeting deadlines.

- Team collaboration improves productivity and results.

Team Reflection: The DevCore team worked collaboratively to complete the project despite challenges. Each  member contributed to their assigned roles, and consistent communication ensured that progress was maintained. The project provided valuable experience in project management, teamwork, and community engagement.