## Gantt
Task ID | Task Name | Start Date | End Date | Duration | Predecessor | Resource | MileStone
1 | Project initiation | 20-03-2026 | 20-03-2026 | 1 day |  | Project Manager | Yes
2 | Identify Dance Groups | 21-03-2026 | 22-03-2026 | 2 days | 1 | Content Director | No
3 | Contact Stakeholders | 23-03-2026 | 24-03-2026 |  | 2 | Comunications Officer | No
4 | Schedule Interviews | 25-03-2026 | 25-03-2026 | 2 days | 3 | Project Manager | Yes
5 | Conduct Interviews and & Record videos | 26-03-2026 | 28-03-2026 | 3 days | 4 | Team Members | No
6 | Collect Photos & content | 29-03-2026 | 30-03-2026 | 2 days | 5 | Content Director | No
7 | Develop Content(editing) | 01-04-2026 | 03-04-2026 | 4 days | 6 | Technical Lead | No
8 | Create Website | 04-04-2026 | 08-04-2026 | 5 days | 7 | Technical Lead | No
9 | Upload & Organise Content | 09-04-2026 | 11-04-2026 | 2 days | 8 | Content Director | No
10 | Prepare Presentation | 12-04-2026 | 13-04-2026 | 2 days | 9 | Team Members | No
11 | Final Review & Submission | 15-04-2026 | 15-04-2026 | 1 day | 10 | Project Manager | Yes